## Sheet1
Task ID | Concerns Functional Requirement ID | Task Description | Sub-Task Description | Allocated to Chen (& Planned Hours) | Allocated to Yan (& Planned Hours) | Allocated to Nick (& Planned Hours)
1 |  | Log in Page
1.1 |  |  | Planning & Research |  |  | 10
1.2 | 1.2.2 |  | Log in & Password Required. |  |  | 10
1.3 | 1.1.1 |  | Forgot Your password link |  |  | 0.5
1.4 | 1.1.9 |  | Responsive to mobile devices |  |  | 4
1.5 | 1.2.1 |  | Ensure compatibility with: Chrome 49 Firefox 44 Internet Explorer 11 Safari 9 |  |  | 5
1.6 | 1.1.1 |  | User Table database queries |  |  | 2
2 |  | Reset Password Page
2.1 | 1.1.1 |  | Enter User Name field | 5
2.2 | 1.1.1 |  | Send email to email address registered to the user name containing a temporary password. | 15
2.3 | 1.1.9 |  | Responsive to mobile devices | 10
2.4 | 1.2.1 |  | Ensure compatibility with: Chrome 49 Firefox 44 Internet Explorer 11 Safari 9 | 5
3 |  | Manage Profile Page
3.1 | 1.1.1 |  | Fields for recording & Displaying required values: Password, Confirm Password, Email Address | 5
3.2 | 1.1.1 |  | Save option for initial registration, editing profile and administrator editing of user details | 10
3.3 | 1.2.9 |  | Responsive to mobile devices | 10
| 1.2.1 |  | Ensure compatibility with: Chrome 49 Firefox 44 Internet Explorer 11 Safari 9 | 5
4 |  | User Edit Page
4.1 | 1.1.3 |  | Display a list of all registered user's with buttons for creating, deleting and modifying each |  | 10
4.2 |  |  | Search option to search by Vendor ID |  | 5
4.3 | 1.1.4 |  | Option to grant Administrator privilege to user |  | 1
4.4 |  |  | Password Encryption/Decryption in Back End |  | 10
4.5 | 1.2.9 |  | Responsive to mobile devices |  | 5
4.6 | 1.2.1 |  | Ensure compatibility with: Chrome 49 Firefox 44 Internet Explorer 11 Safari 9 |  | 3
5 |  | User Home Page
5.1 |  |  | Planning & Research |  |  | 10
5.2 | 1.1.7 |  | List of all invoices for vendor (Reference, Document Date, Status, Curtin Document Reference. Narration dependent on device width) |  |  | 5
5.3 | 1.1.8 |  | Button/Option to open selected invoice |  |  | 1
5.4 |  |  | Link to edit profile. |  |  | 0.5
5.5 | 1.1.9 |  | Responsive to mobile devices |  |  | 4
5.6 | 1.2.1 |  | Ensure compatibility with: Chrome 49 Firefox 44 Internet Explorer 11 Safari 9 |  |  | 5
5.7 | 1.1.7 |  | Finance One query to return invoice details for vendor |  |  | 0.5
6 |  | Invoice Detail View Page
6.1 | 3.1.8 |  | Display relevant details for invoice (Reference, Document Date, Status, Stage, Department currently in possession of invoice, contact number for department, email address of department) |  | 10
6.2 |  |  | Return to List button |  | 0.5
6.3 | 1.1.9 |  | Responsive to mobile devices |  | 5
6.4 | 1.2.1 |  | Ensure compatibility with: Chrome 49 Firefox 44 Internet Explorer 11 Safari 9 |  | 3
7 |  | Database Table Creation
7.1 |  |  | User Table |  |  | 0.5
7.2 | 8.1 |  | Faculty Contact Table [Extension] |  | 0.5
8 |  | Back End Development
8.3 | 1.3.1 |  | Database Sanitisation of all Input |  | 10
9 |  | Documentation
9.1 | 4.1.1.a |  | Create User Manual |  |  | 4
9.2 | 4.1.1.b |  | Create Technical Manual | 5 | 2 | 2
9.3 |  |  | Requirements Document |  |  | 4
9.4 |  |  | Task Allocation Document |  |  | 4
9.5 |  |  | Meeting Minutes |  |  | 10
|  |  | Total Hours | 70 | 65 | 82